## Sheet1
Task | Subtask | Time Estimate (in days) | Comments
Determine platform
| Live video research | 0.5 | Format and resolutions supported?
| Recorded video research | 0.5 | Format and resolutions supported?
| Q and A research | 0.5 | Something like Discord along with prerecorded video?
General Outline
| Create | 0 | Done.
| Gather feedback | 0.5 | GTRI internal, of course. Who else? NMO? Stratcom? NTAC?
| Modify | 0.5
Detailed Outline
| Create | 1.5
| Approval | 0.5 | Is GTRI internal approval enough?
Build out IEPD |  | 1.5 | Assuming Crash Driver as a base
Create/modify existing slides for static content |  | 1.5
XML examples
| Create XML examples | 1
| Break into chunks to be pasted live | 0.25
JSON-LD examples? |  |  | We don't want to spend a lot of time on JSON, but quickly viewing matching examples would be a start.
| Create JSON-LD examples? | 1
| Break into chunks to be pasted live | 0.25
Test Run |  | 2 | Limited audience? Wider audience, but billed as a test run?
Total |  | 12